FOOTBALL Report

**Introduction**

Project Description: The football project involves coordinating with teams, securing a venue, promoting the event, and managing logistics on the day of the match. Project Scope: The overall tasks related to the project include team recruitment, marketing, ticket sales, and event management.

**Application**

Background information related to the project: The football project was initiated to support the community youth sports program and promote physical activity and teamwork.

**Schedule**

**Work Schedule: The project is currently on schedule with team recruitment and venue booking completed. The promotion and ticket sales phase is currently underway, with the match scheduled for next month.**

**Work Status**

**1.Work Completed Before This Report: Team recruitment and venue booking**

**2.Work Completed During This Time Period: Promotional materials prepared, ticket sales launched**

**3.Work to Complete Before Finishing the Project: Finalizing match logistics, coordinating with volunteers**

**Problems**

**Unexpected Developments: A sponsor withdrew support, affecting our budget**

**Plan to Correct Problems: Seeking alternative sponsorships, cutting costs where possible**

**Conclusion**

In conclusion, the football project is progressing well, despite some challenges with sponsorships. The project is currently on schedule, and efforts are being made to address any issues that may arise. Thank you for your continued support and guidance in this project.